## Tracker
Category | Task | Owner | Status | Priority
Core Platform | Homepage structure & CTAs | Frontend Dev | Not Started | High
Core Platform | Service Request Flow | Backend Dev | In Progress | High
Core Platform | User Accounts & Dashboard | Backend Dev | In Progress | Medium
Subscriptions | Subscription Plan Pages | Frontend Dev | Not Started | High
Subscriptions | Recurring Billing Integration | Backend Dev | Not Started | High
Service Providers | Provider Onboarding Portal | Backend Dev | Not Started | Medium
Service Providers | Provider Dashboard & Job Assignment | Backend Dev | Not Started | Medium
Referral Program | Referral Tracking System | Backend Dev | Not Started | High
Referral Program | Referral Rewards & Anti-fraud Checks | Backend Dev | Not Started | Medium
Membership Program | Membership Tiers Design | Frontend Dev | Not Started | Medium
Membership Program | Member Perks (Discounts, Priority Support) | Backend Dev | Not Started | Low
Compliance & Trust | Compliance Badges & SLA Page | Frontend Dev | Not Started | High
Compliance & Trust | Data Privacy & Secure Login | Backend Dev | Not Started | High
Social Impact | Social Pledge Counter (1-for-10) | Frontend Dev | Not Started | High
Social Impact | Impact/ESG Page (quarterly reports) | Frontend Dev | Not Started | Medium
Content & Marketing | SEO Optimization & FAQ | Frontend Dev | Not Started | Medium
Content & Marketing | Marketing Landing Pages (MCST/SME) | Frontend Dev | Not Started | Medium
Testing & Launch | Staging Deployment | DevOps | Not Started | High
Testing & Launch | UAT & Final Launch | QA/Team | Not Started | High
Events | Volunteer Recruitment (Workshop Trainers) | Backend Dev | Not Started | High
Events | Resident Signup (Event Registration) | Frontend Dev | Not Started | High
Events | Event Countdown Timer | Frontend Dev | Not Started | Medium
User Roles & Dashboards | Roles & Permissions Matrix | Backend Dev | Not Started | High
User Roles & Dashboards | Dashboard: User | Frontend Dev | Not Started | High
User Roles & Dashboards | Dashboard: Subscription User | Frontend Dev | Not Started | High
User Roles & Dashboards | Dashboard: Referral | Frontend Dev | Not Started | Medium
User Roles & Dashboards | Dashboard: Vendor | Frontend Dev | Not Started | High
User Roles & Dashboards | Dashboard: Admin | Frontend Dev | Not Started | High
User Roles & Dashboards | Dashboard: Super Admin | Frontend Dev | Not Started | High

## Timeline
Category | Task | Owner | Status | Priority | Start Date | End Date
Core Platform | Homepage structure & CTAs | Frontend Dev | Not Started | High | 2025-08-25 | 2025-09-01
Core Platform | Service Request Flow | Backend Dev | In Progress | High | 2025-08-25 | 2025-09-15
Core Platform | User Accounts & Dashboard | Backend Dev | In Progress | Medium | 2025-09-01 | 2025-09-22
Subscriptions | Subscription Plan Pages | Frontend Dev | Not Started | High | 2025-09-08 | 2025-09-22
Subscriptions | Recurring Billing Integration | Backend Dev | Not Started | High | 2025-09-15 | 2025-09-29
Service Providers | Provider Onboarding Portal | Backend Dev | Not Started | Medium | 2025-09-22 | 2025-10-06
Service Providers | Provider Dashboard & Job Assignment | Backend Dev | Not Started | Medium | 2025-09-29 | 2025-10-13
Referral Program | Referral Tracking System | Backend Dev | Not Started | High | 2025-10-06 | 2025-10-20
Referral Program | Referral Rewards & Anti-fraud Checks | Backend Dev | Not Started | Medium | 2025-10-13 | 2025-10-27
Membership Program | Membership Tiers Design | Frontend Dev | Not Started | Medium | 2025-10-20 | 2025-11-03
Membership Program | Member Perks (Discounts, Priority Support) | Backend Dev | Not Started | Low | 2025-10-27 | 2025-11-10
Compliance & Trust | Compliance Badges & SLA Page | Frontend Dev | Not Started | High | 2025-11-03 | 2025-11-17
Compliance & Trust | Data Privacy & Secure Login | Backend Dev | Not Started | High | 2025-11-10 | 2025-11-24
Social Impact | Social Pledge Counter (1-for-10) | Frontend Dev | Not Started | High | 2025-11-17 | 2025-12-01
Social Impact | Impact/ESG Page (quarterly reports) | Frontend Dev | Not Started | Medium | 2025-11-24 | 2025-12-08
Content & Marketing | SEO Optimization & FAQ | Frontend Dev | Not Started | Medium | 2025-12-01 | 2025-12-15
Content & Marketing | Marketing Landing Pages (MCST/SME) | Frontend Dev | Not Started | Medium | 2025-12-08 | 2025-12-22
Testing & Launch | Staging Deployment | DevOps | Not Started | High | 2025-12-15 | 2025-12-29
Testing & Launch | UAT & Final Launch | QA/Team | Not Started | High | 2025-12-22 | 2026-01-05
Events | Volunteer Recruitment (Workshop Trainers) | Backend Dev | Not Started | High | 2026-01-06 | 2026-01-20
Events | Resident Signup (Event Registration) | Frontend Dev | Not Started | High | 2026-01-09 | 2026-01-19
Events | Event Countdown Timer | Frontend Dev | Not Started | Medium | 2026-01-12 | 2026-01-19
User Roles & Dashboards | Roles & Permissions Matrix | Backend Dev | Not Started | High | 2026-01-15 | 2026-01-22
User Roles & Dashboards | Dashboard: User | Frontend Dev | Not Started | High | 2026-01-18 | 2026-01-25
User Roles & Dashboards | Dashboard: Subscription User | Frontend Dev | Not Started | High | 2026-01-21 | 2026-01-28
User Roles & Dashboards | Dashboard: Referral | Frontend Dev | Not Started | Medium | 2026-01-24 | 2026-01-31
User Roles & Dashboards | Dashboard: Vendor | Frontend Dev | Not Started | High | 2026-01-27 | 2026-02-06
User Roles & Dashboards | Dashboard: Admin | Frontend Dev | Not Started | High | 2026-01-30 | 2026-02-09
User Roles & Dashboards | Dashboard: Super Admin | Frontend Dev | Not Started | High | 2026-02-02 | 2026-02-12

## Microtasks
Category | Task | Micro Task | Owner | Priority | Start Date | End Date | Status
Core Platform | Homepage structure & CTAs | Design hero banner | Frontend Dev | High | 2025-08-25 | 2025-08-26 | Not Started
Core Platform | Homepage structure & CTAs | Add subscription CTA | Frontend Dev | High | 2025-08-26 | 2025-08-28 | Not Started
Core Platform | Homepage structure & CTAs | Implement navigation bar | Frontend Dev | High | 2025-08-28 | 2025-08-30 | Not Started
Core Platform | Homepage structure & CTAs | Responsive layout check | Frontend Dev | High | 2025-08-30 | 2025-09-01 | Not Started
Core Platform | Service Request Flow | Create multi-step form | Backend Dev | High | 2025-08-25 | 2025-08-30 | Not Started
Core Platform | Service Request Flow | Add location auto-fill | Backend Dev | High | 2025-08-30 | 2025-09-04 | Not Started
Core Platform | Service Request Flow | Implement media upload | Backend Dev | High | 2025-09-04 | 2025-09-09 | Not Started
Core Platform | Service Request Flow | Review & submit screen | Backend Dev | High | 2025-09-09 | 2025-09-15 | Not Started
Core Platform | User Accounts & Dashboard | Profile page | Backend Dev | Medium | 2025-09-01 | 2025-09-06 | Not Started
Core Platform | User Accounts & Dashboard | Order history | Backend Dev | Medium | 2025-09-06 | 2025-09-11 | Not Started
Core Platform | User Accounts & Dashboard | Referral link | Backend Dev | Medium | 2025-09-11 | 2025-09-16 | Not Started
Core Platform | User Accounts & Dashboard | Password reset | Backend Dev | Medium | 2025-09-16 | 2025-09-22 | Not Started
Subscriptions | Subscription Plan Pages | Design plan cards | Frontend Dev | High | 2025-09-08 | 2025-09-11 | Not Started
Subscriptions | Subscription Plan Pages | Add benefits list | Frontend Dev | High | 2025-09-11 | 2025-09-15 | Not Started
Subscriptions | Subscription Plan Pages | CTA to checkout | Frontend Dev | High | 2025-09-15 | 2025-09-18 | Not Started
Subscriptions | Subscription Plan Pages | Mobile responsiveness | Frontend Dev | High | 2025-09-18 | 2025-09-22 | Not Started
Subscriptions | Recurring Billing Integration | Stripe setup | Backend Dev | High | 2025-09-15 | 2025-09-18 | Not Started
Subscriptions | Recurring Billing Integration | Recurring payments | Backend Dev | High | 2025-09-18 | 2025-09-22 | Not Started
Subscriptions | Recurring Billing Integration | Proration & cancel | Backend Dev | High | 2025-09-22 | 2025-09-25 | Not Started
Subscriptions | Recurring Billing Integration | Billing history page | Backend Dev | High | 2025-09-25 | 2025-09-29 | Not Started
Service Providers | Provider Onboarding Portal | Signup form | Backend Dev | Medium | 2025-09-22 | 2025-09-25 | Not Started
Service Providers | Provider Onboarding Portal | KYC upload | Backend Dev | Medium | 2025-09-25 | 2025-09-29 | Not Started
Service Providers | Provider Onboarding Portal | Skills & services | Backend Dev | Medium | 2025-09-29 | 2025-10-02 | Not Started
Service Providers | Provider Onboarding Portal | Approval workflow | Backend Dev | Medium | 2025-10-02 | 2025-10-06 | Not Started
Service Providers | Provider Dashboard & Job Assignment | Job list view | Backend Dev | Medium | 2025-09-29 | 2025-10-02 | Not Started
Service Providers | Provider Dashboard & Job Assignment | Accept/reject jobs | Backend Dev | Medium | 2025-10-02 | 2025-10-06 | Not Started
Service Providers | Provider Dashboard & Job Assignment | Calendar integration | Backend Dev | Medium | 2025-10-06 | 2025-10-09 | Not Started
Service Providers | Provider Dashboard & Job Assignment | Earnings summary | Backend Dev | Medium | 2025-10-09 | 2025-10-13 | Not Started
Referral Program | Referral Tracking System | Generate referral links | Backend Dev | High | 2025-10-06 | 2025-10-09 | Not Started
Referral Program | Referral Tracking System | Track clicks & signups | Backend Dev | High | 2025-10-09 | 2025-10-13 | Not Started
Referral Program | Referral Tracking System | Database schema | Backend Dev | High | 2025-10-13 | 2025-10-16 | Not Started
Referral Program | Referral Tracking System | Admin report | Backend Dev | High | 2025-10-16 | 2025-10-20 | Not Started
Referral Program | Referral Rewards & Anti-fraud Checks | Reward triggers | Backend Dev | Medium | 2025-10-13 | 2025-10-16 | Not Started
Referral Program | Referral Rewards & Anti-fraud Checks | Fraud detection rules | Backend Dev | Medium | 2025-10-16 | 2025-10-20 | Not Started
Referral Program | Referral Rewards & Anti-fraud Checks | User wallet view | Backend Dev | Medium | 2025-10-20 | 2025-10-23 | Not Started
Referral Program | Referral Rewards & Anti-fraud Checks | Notification system | Backend Dev | Medium | 2025-10-23 | 2025-10-27 | Not Started
Membership Program | Membership Tiers Design | Define tier benefits | Frontend Dev | Medium | 2025-10-20 | 2025-10-23 | Not Started
Membership Program | Membership Tiers Design | Design tier UI | Frontend Dev | Medium | 2025-10-23 | 2025-10-27 | Not Started
Membership Program | Membership Tiers Design | Display perks in dashboard | Frontend Dev | Medium | 2025-10-27 | 2025-10-30 | Not Started
Membership Program | Membership Tiers Design | Upgrade/downgrade flow | Frontend Dev | Medium | 2025-10-30 | 2025-11-03 | Not Started
Membership Program | Member Perks (Discounts, Priority Support) | Discount logic in checkout | Backend Dev | Low | 2025-10-27 | 2025-10-30 | Not Started
Membership Program | Member Perks (Discounts, Priority Support) | Priority support flag | Backend Dev | Low | 2025-10-30 | 2025-11-03 | Not Started
Membership Program | Member Perks (Discounts, Priority Support) | UI badges | Backend Dev | Low | 2025-11-03 | 2025-11-06 | Not Started
Membership Program | Member Perks (Discounts, Priority Support) | Testing cases | Backend Dev | Low | 2025-11-06 | 2025-11-10 | Not Started
Compliance & Trust | Compliance Badges & SLA Page | Collect compliance logos | Frontend Dev | High | 2025-11-03 | 2025-11-06 | Not Started
Compliance & Trust | Compliance Badges & SLA Page | Design SLA section | Frontend Dev | High | 2025-11-06 | 2025-11-10 | Not Started
Compliance & Trust | Compliance Badges & SLA Page | Add SLA link to footer | Frontend Dev | High | 2025-11-10 | 2025-11-13 | Not Started
Compliance & Trust | Compliance Badges & SLA Page | Legal review | Frontend Dev | High | 2025-11-13 | 2025-11-17 | Not Started
Compliance & Trust | Data Privacy & Secure Login | Implement JWT auth | Backend Dev | High | 2025-11-10 | 2025-11-13 | Not Started
Compliance & Trust | Data Privacy & Secure Login | Password hashing | Backend Dev | High | 2025-11-13 | 2025-11-17 | Not Started
Compliance & Trust | Data Privacy & Secure Login | Session timeout | Backend Dev | High | 2025-11-17 | 2025-11-20 | Not Started
Compliance & Trust | Data Privacy & Secure Login | 2FA integration | Backend Dev | High | 2025-11-20 | 2025-11-24 | Not Started
Social Impact | Social Pledge Counter (1-for-10) | Impact counter design | Frontend Dev | High | 2025-11-17 | 2025-11-20 | Not Started
Social Impact | Social Pledge Counter (1-for-10) | Backend logic | Frontend Dev | High | 2025-11-20 | 2025-11-24 | Not Started
Social Impact | Social Pledge Counter (1-for-10) | Admin update panel | Frontend Dev | High | 2025-11-24 | 2025-11-27 | Not Started
Social Impact | Social Pledge Counter (1-for-10) | Frontend integration | Frontend Dev | High | 2025-11-27 | 2025-12-01 | Not Started
Social Impact | Impact/ESG Page (quarterly reports) | Page layout | Frontend Dev | Medium | 2025-11-24 | 2025-11-27 | Not Started
Social Impact | Impact/ESG Page (quarterly reports) | Placeholder charts | Frontend Dev | Medium | 2025-11-27 | 2025-12-01 | Not Started
Social Impact | Impact/ESG Page (quarterly reports) | Quarterly template | Frontend Dev | Medium | 2025-12-01 | 2025-12-04 | Not Started
Social Impact | Impact/ESG Page (quarterly reports) | Link from footer | Frontend Dev | Medium | 2025-12-04 | 2025-12-08 | Not Started
Content & Marketing | SEO Optimization & FAQ | Meta tags setup | Frontend Dev | Medium | 2025-12-01 | 2025-12-04 | Not Started
Content & Marketing | SEO Optimization & FAQ | SEO audit fixes | Frontend Dev | Medium | 2025-12-04 | 2025-12-08 | Not Started
Content & Marketing | SEO Optimization & FAQ | FAQ structure | Frontend Dev | Medium | 2025-12-08 | 2025-12-11 | Not Started
Content & Marketing | SEO Optimization & FAQ | FAQ search bar | Frontend Dev | Medium | 2025-12-11 | 2025-12-15 | Not Started
Content & Marketing | Marketing Landing Pages (MCST/SME) | Design B2B page | Frontend Dev | Medium | 2025-12-08 | 2025-12-11 | Not Started
Content & Marketing | Marketing Landing Pages (MCST/SME) | Add workshop CTA | Frontend Dev | Medium | 2025-12-11 | 2025-12-15 | Not Started
Content & Marketing | Marketing Landing Pages (MCST/SME) | Case study section | Frontend Dev | Medium | 2025-12-15 | 2025-12-18 | Not Started
Content & Marketing | Marketing Landing Pages (MCST/SME) | Contact form | Frontend Dev | Medium | 2025-12-18 | 2025-12-22 | Not Started
Testing & Launch | Staging Deployment | Setup staging server | DevOps | High | 2025-12-15 | 2025-12-18 | Not Started
Testing & Launch | Staging Deployment | Deploy backend | DevOps | High | 2025-12-18 | 2025-12-22 | Not Started
Testing & Launch | Staging Deployment | Deploy frontend | DevOps | High | 2025-12-22 | 2025-12-25 | Not Started
Testing & Launch | Staging Deployment | Smoke testing | DevOps | High | 2025-12-25 | 2025-12-29 | Not Started
Testing & Launch | UAT & Final Launch | Collect feedback | QA/Team | High | 2025-12-22 | 2025-12-25 | Not Started
Testing & Launch | UAT & Final Launch | Bug fixes | QA/Team | High | 2025-12-25 | 2025-12-29 | Not Started
Testing & Launch | UAT & Final Launch | Final polish | QA/Team | High | 2025-12-29 | 2026-01-01 | Not Started
Testing & Launch | UAT & Final Launch | Go live checklist | QA/Team | High | 2026-01-01 | 2026-01-05 | Not Started
Events | Volunteer Recruitment (Workshop Trainers) | Define trainer criteria & roles | Backend Dev | High | 2026-01-06 | 2026-01-09 | Not Started
Events | Volunteer Recruitment (Workshop Trainers) | Create recruitment landing page | Backend Dev | High | 2026-01-09 | 2026-01-12 | Not Started
Events | Volunteer Recruitment (Workshop Trainers) | Application form + KYC upload | Backend Dev | High | 2026-01-12 | 2026-01-15 | Not Started
Events | Volunteer Recruitment (Workshop Trainers) | Admin review & approval flow | Backend Dev | High | 2026-01-15 | 2026-01-18 | Not Started
Events | Resident Signup (Event Registration) | Event list & details page | Frontend Dev | High | 2026-01-09 | 2026-01-11 | Not Started
Events | Resident Signup (Event Registration) | Signup form + email confirmation | Frontend Dev | High | 2026-01-11 | 2026-01-13 | Not Started
Events | Resident Signup (Event Registration) | Capacity limits & waitlist | Frontend Dev | High | 2026-01-13 | 2026-01-15 | Not Started
Events | Resident Signup (Event Registration) | Export attendee CSV for ops | Frontend Dev | High | 2026-01-15 | 2026-01-17 | Not Started
Events | Event Countdown Timer | Reusable countdown component | Frontend Dev | Medium | 2026-01-12 | 2026-01-13 | Not Started
Events | Event Countdown Timer | Admin set event start/end | Frontend Dev | Medium | 2026-01-13 | 2026-01-14 | Not Started
Events | Event Countdown Timer | Edge cases (past events) | Frontend Dev | Medium | 2026-01-14 | 2026-01-15 | Not Started
Events | Event Countdown Timer | Accessibility & tests | Frontend Dev | Medium | 2026-01-15 | 2026-01-16 | Not Started
User Roles & Dashboards | Roles & Permissions Matrix | Define role capabilities | Backend Dev | High | 2026-01-15 | 2026-01-16 | Not Started
User Roles & Dashboards | Roles & Permissions Matrix | DB schema for roles/permissions | Backend Dev | High | 2026-01-16 | 2026-01-17 | Not Started
User Roles & Dashboards | Roles & Permissions Matrix | Seed roles in dev/staging | Backend Dev | High | 2026-01-17 | 2026-01-18 | Not Started
User Roles & Dashboards | Roles & Permissions Matrix | Middleware/guards for routes | Backend Dev | High | 2026-01-18 | 2026-01-19 | Not Started
User Roles & Dashboards | Dashboard: User | Overview (tickets, orders) | Frontend Dev | High | 2026-01-18 | 2026-01-19 | Not Started
User Roles & Dashboards | Dashboard: User | Profile quick actions | Frontend Dev | High | 2026-01-19 | 2026-01-20 | Not Started
User Roles & Dashboards | Dashboard: User | Notifications | Frontend Dev | High | 2026-01-20 | 2026-01-21 | Not Started
User Roles & Dashboards | Dashboard: User | Empty states | Frontend Dev | High | 2026-01-21 | 2026-01-22 | Not Started
User Roles & Dashboards | Dashboard: Subscription User | Subscription status widget | Frontend Dev | High | 2026-01-21 | 2026-01-22 | Not Started
User Roles & Dashboards | Dashboard: Subscription User | Next visit & SLA card | Frontend Dev | High | 2026-01-22 | 2026-01-23 | Not Started
User Roles & Dashboards | Dashboard: Subscription User | Manage plan (pause/cancel) | Frontend Dev | High | 2026-01-23 | 2026-01-24 | Not Started
User Roles & Dashboards | Dashboard: Subscription User | Billing history | Frontend Dev | High | 2026-01-24 | 2026-01-25 | Not Started
User Roles & Dashboards | Dashboard: Referral | Referral link & stats | Frontend Dev | Medium | 2026-01-24 | 2026-01-25 | Not Started
User Roles & Dashboards | Dashboard: Referral | Reward balance & payouts | Frontend Dev | Medium | 2026-01-25 | 2026-01-26 | Not Started
User Roles & Dashboards | Dashboard: Referral | Fraud flags surface | Frontend Dev | Medium | 2026-01-26 | 2026-01-27 | Not Started
User Roles & Dashboards | Dashboard: Referral | Share templates | Frontend Dev | Medium | 2026-01-27 | 2026-01-28 | Not Started
User Roles & Dashboards | Dashboard: Vendor | Job queue & calendar | Frontend Dev | High | 2026-01-27 | 2026-01-29 | Not Started
User Roles & Dashboards | Dashboard: Vendor | Accept/reject & SLA timers | Frontend Dev | High | 2026-01-29 | 2026-01-31 | Not Started
User Roles & Dashboards | Dashboard: Vendor | Earnings & payouts | Frontend Dev | High | 2026-01-31 | 2026-02-02 | Not Started
User Roles & Dashboards | Dashboard: Vendor | Compliance/KYC status | Frontend Dev | High | 2026-02-02 | 2026-02-04 | Not Started
User Roles & Dashboards | Dashboard: Admin | Orders & tickets overview | Frontend Dev | High | 2026-01-30 | 2026-02-01 | Not Started
User Roles & Dashboards | Dashboard: Admin | User management | Frontend Dev | High | 2026-02-01 | 2026-02-03 | Not Started
User Roles & Dashboards | Dashboard: Admin | Content admin (FAQ, banners) | Frontend Dev | High | 2026-02-03 | 2026-02-05 | Not Started
User Roles & Dashboards | Dashboard: Admin | Impact counter controls | Frontend Dev | High | 2026-02-05 | 2026-02-07 | Not Started
User Roles & Dashboards | Dashboard: Super Admin | Role management | Frontend Dev | High | 2026-02-02 | 2026-02-04 | Not Started
User Roles & Dashboards | Dashboard: Super Admin | Vendor onboarding approvals | Frontend Dev | High | 2026-02-04 | 2026-02-06 | Not Started
User Roles & Dashboards | Dashboard: Super Admin | System settings | Frontend Dev | High | 2026-02-06 | 2026-02-08 | Not Started
User Roles & Dashboards | Dashboard: Super Admin | Audit logs | Frontend Dev | High | 2026-02-08 | 2026-02-10 | Not Started

## Roles_Permissions
Role | Can View | Can Create | Can Edit | Can Approve | Can Assign Jobs | Access Billing | Access Impact | Manage Users | Manage Vendors | Access Admin Console
user | Yes | Yes | Yes | No | No | No | No | No | No | No
subscription user | Yes | Yes | Yes | No | No | Yes | Yes | No | No | No
referral | Yes | Yes | Yes | No | No | No | No | No | No | No
vendor | Yes | Yes | Yes | Yes | Yes | No | No | No | Yes | No
admin | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
super admin | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes