## Swift Fix Pro
Task ID | Task Description | Status | Assign To | Description
1 | Project Initiation and Planning
2 | Define project scope and objectives |  |  | The Handyman Portal Development project aims to create a user-friendly website that facilitates handyman services. The portal will cater to both users seeking handyman services and vendors offering these services. Key features as below
3 | Create a detailed project timeline |  |  | Develop a fully functional handyman portal website within the stipulated timeline. Ensure user-friendly navigation and accessibility for both users and vendors. Implement a robust membership and referral system to enhance user engagement. Integrate WhatsApp and chatbot features to improve communication and support.
4 | Assign roles and responsibilities
5 | Website Setup and Configuration
6 | Install necessary dependancies
7 | Set up database and admin credentials
8 | Configure basic settings (language, timezone, etc.)
9 | Choose and customize website theme
10 | Core Website Development
11 | Design and implement site structure and navigation
12 | Create essential pages (Home, About, Contact, Services)
13 | Implement responsive design for mobile compatibility
14 | Set up SEO basics (meta tags, sitemap)
15 | User Management and Authentication
16 | Define user roles (admin, member, handyman, client)
17 | Implement registration and login system
18 | Set up role-based permissions
19 | Handyman Portal Features
20 | a. Membership System |  |  | Membership system for users, referral and vendors.
21 | Create membership levels and pricing
22 | Implement purchase and renewal process
23 | Set up access controls based on membership
24 | b. Job Request System
25 | Design and implement job request form
26 | Create job matching algorithm
27 | Implement rating and review system
28 | c. Vendor (Handyman) Management |  |  | Configuration for handyman (vendor) profiles, including service offerings, availability, and pricing.
29 | Create vendor registration and verification process
30 | Set up vendor profiles and portfolios
31 | Implement search and filter system for clients
32 | Advanced Features Implementation
33 | a. Chatbot for Enquiries:
34 | Research and select a chatbot integration compatible with
35 | Design conversation flows for common inquiries
36 | Implement and test the chatbot
37 | Set up handoff to human support when needed
38 | b. Referral System |  |  | Referral system to encourage user engagement and service sharing.
39 | Design 3-tier commission structure
40 | Implement referral tracking and dashboard
41 | Set up commission calculation and payout system
42 | c. Payment and Financial Integration
43 | Set up payment gateway for memberships and transactions
44 | Implement secure payment processing
45 | Configure commission payouts for referrals
46 | b. AI-Powered Chatbot
47 | Integrate AI chatbot (e.g., GPT-based)
48 | Train on handyman-specific knowledge
49 | Implement fallback options and human handoff
50 | Analytics and Reporting
51 | Integrate analytics tools (e.g., Google Analytics)
52 | Create admin dashboards for monitoring
53 | Set up custom reports for business insights
54 | Security and Compliance
55 | Implement SSL certificate
56 | Set up regular backup procedures
57 | Draft and implement legal documents (ToS, Privacy Policy)
58 | Ensure compliance with local service marketplace regulations
59 | Testing and Quality Assurance
60 | Conduct thorough functionality testing
61 | Perform security and performance testing
62 | User acceptance testing with sample users
63 | Launch Preparation and Execution
64 | Prepare marketing materials and launch strategy
65 | Set up domain and DNS
66 | Conduct soft launch for initial feedback
67 | Execute full launch with marketing campaign
68 | Post-Launch Activities
69 | Monitor system performance and user feedback
70 | Address bugs and issues promptly
71 | Plan for regular updates and feature enhancements
72 | Plan for regular updates and maintenance
Phase 2 | WhatsApp Integration and CRM Enhancement
1 | WhatsApp Business API Setup
2 | Apply for WhatsApp Business API access
3 | Set up WhatsApp Business account
4 | Configure WhatsApp Business profile (about, business hours, etc.)
5 | WhatsApp Integration
6 | Research and select appropriate WhatsApp integration module
7 | Install and configure the WhatsApp module in
8 | Set up authentication and connection between and WhatsApp
9 | CRM Integration
10 | Link WhatsApp conversations to CRM records
11 | Set up automatic lead/contact creation from WhatsApp chats
12 | Implement WhatsApp messaging directly from CRM interface
13 | Automated Messaging Features
14 | Set up welcome messages for new contacts
15 | Create automated responses for frequently asked questions
16 | Implement appointment reminders via WhatsApp
17 | WhatsApp Commerce Integration
18 | a. Inventory Management
19 | Upload inventory to Meta using the API or Meta Commerce Manager
20 | Ensure product details are accurate and up-to-date
21 | Set up regular inventory sync between and Meta
22 | b. Catalog Connection
23 | Create and categorize an Ecommerce catalog in Meta Commerce Manager
24 | Connect the Ecommerce catalog to the WhatsApp Business Account
25 | Verify catalog visibility and accuracy
26 | c. Commerce Settings Configuration
27 | Set up commerce settings for the business phone number
28 | Configure payment options and shipping preferences
29 | Ensure compliance with Meta's commerce policies
30 | d. Product Sharing Implementation
31 | Develop functionality to send Multi-Product Messages
32 | Implement Single Product Message sharing
33 | Create templates for product showcases
34 | e. Customer Interaction Handling
35 | Set up webhooks to receive customer questions and orders
36 | Implement automated responses for common product inquiries
37 | Develop a system to route product-specific queries to appropriate staff
38 | f. Shopping Cart Integration
39 | Enable customers to add products to cart within WhatsApp chat
40 | Implement seamless transition between browsing and purchasing
41 | Ensure cart synchronization between WhatsApp and
42 | g. Order Processing
43 | Develop order confirmation process via WhatsApp
44 | Implement order status updates through WhatsApp messages
45 | Create system for handling order modifications and cancellations
46 | h. Product Recommendations
47 | Implement AI-driven product recommendation system
48 | Develop personalized product suggestion messages
49 | Set up triggers for sending relevant product recommendations
50 | i. Analytics for Commerce
51 | Set up tracking for product views, cart additions, and purchases via WhatsApp
52 | Create dashboards for monitoring WhatsApp commerce performance
53 | Implement A/B testing for product presentation strategies
54 | j. Language Optimization
55 | Ensure all product information and commerce interactions are in English
56 | Implement natural language processing to understand product inquiries
57 | Develop a glossary of product-specific terms for consistent communication
58 | k. Testing and Quality Assurance
59 | Conduct thorough testing of the entire purchase flow via WhatsApp
60 | Perform user acceptance testing with a sample group of customers
61 | Test edge cases such as out-of-stock items and pricing changes
62 | l. Customer Support for Commerce
63 | Train support staff on handling product-related inquiries via WhatsApp
64 | Implement quick access to product information for support agents
65 | Develop scripts for common commerce-related customer interactions
66 | m. Launch and Optimization
67 | Plan a phased rollout of WhatsApp commerce features
68 | Monitor early transactions and customer feedback
69 | Continuously optimize product presentation and purchase flow based on data
70 | Customer Support via WhatsApp
71 | Set up WhatsApp as a customer support channel
72 | Implement ticket creation from WhatsApp conversations
73 | Develop a system for routing WhatsApp inquiries to appropriate team members
74 | WhatsApp Payment Integration
75 | Research WhatsApp payment capabilities in your area
76 | Integrate WhatsApp payments with your existing payment system
77 | Set up secure transaction processes
78 | Multi-Agent Support
79 | Implement a system for multiple agents to handle WhatsApp conversations
80 | Set up agent availability and workload distribution
81 | Develop internal chat transfer capabilities between agents
82 | Analytics and Reporting
83 | Set up tracking for WhatsApp message metrics (sent, delivered, read)
84 | Integrate WhatsApp data into existing CRM reports
85 | Create dashboards for WhatsApp performance analytics
86 | Chatbot Integration with WhatsApp
87 | Adapt existing AI chatbot to work with WhatsApp
88 | Implement handoff from chatbot to human agents on WhatsApp
89 | Test and refine chatbot performance on WhatsApp platform
90 | File and Media Sharing
91 | Enable secure file and media sharing through WhatsApp
92 | Implement automatic saving of shared files to CRM records
93 | Set up virus scanning for incoming files
94 | WhatsApp Status Updates
95 | Develop a strategy for using WhatsApp Status feature
96 | Create a content calendar for WhatsApp Status updates
97 | Implement tracking for Status view analytics
98 | Language Support
99 | Ensure all WhatsApp communications support English
100 | Set up language detection for incoming messages
101 | Implement translation services if needed for non-English speakers
102 | Compliance and Data Protection
103 | Review and ensure compliance with WhatsApp Business policies
104 | Implement data protection measures for WhatsApp conversations
105 | Update privacy policy to include WhatsApp data handling
106 | Testing and Quality Assurance
107 | Conduct thorough testing of all WhatsApp features
108 | Perform load testing to ensure system can handle high message volumes
109 | User acceptance testing with a sample group of customers and handymen
110 | Training and Documentation
111 | Create user manuals for staff on WhatsApp integration features
112 | Conduct training sessions for customer support team
113 | Develop FAQ and help documentation for customers
114 | Launch and Monitoring
115 | Plan a phased rollout of WhatsApp features
116 | Monitor system performance and user adoption
117 | Gather feedback and plan for iterative improvements
118 | Ongoing Optimization
119 | Regularly review WhatsApp analytics and user feedback
120 | Continuously improve automated responses and chatbot performance
121 | Stay updated with new WhatsApp Business features and integrate as relevant